Wedding To-Do List
The whole engagement in five stretches, pre-filled with the tasks every wedding has. Add your own on the blank lines.
	Name(s)
	
	The date
	



	12+ MONTHS OUT


	☐
	To do
	Notes
	Due

	☐
	Set the budget
	
	

	☐
	Draft the guest list
	
	

	☐
	Choose the date
	
	

	☐
	Book the venue
	
	

	☐
	Book the officiant
	
	

	☐
	Hire the photographer
	
	

	☐
	Start the dress / suit search
	
	

	☐
	Book caterer or confirm venue catering
	
	

	☐
	
	
	



	6–9 MONTHS OUT


	☐
	To do
	Notes
	Due

	☐
	Send save-the-dates
	
	

	☐
	Book florist and music
	
	

	☐
	Order the dress / suit
	
	

	☐
	Reserve hotel room blocks
	
	

	☐
	Plan the honeymoon
	
	

	☐
	Register for gifts
	
	

	☐
	
	
	



	3 MONTHS OUT


	☐
	To do
	Notes
	Due

	☐
	Order invitations
	
	

	☐
	Book hair and makeup trial
	
	

	☐
	Choose the cake
	
	

	☐
	Buy the rings
	
	

	☐
	Arrange transport
	
	

	☐
	Write the ceremony
	
	

	☐
	
	
	



	1 MONTH OUT


	☐
	To do
	Notes
	Due

	☐
	Mail invitations (6–8 weeks)
	
	

	☐
	Final dress / suit fitting
	
	

	☐
	Confirm all vendors
	
	

	☐
	Apply for the marriage license
	
	

	☐
	Make the seating chart
	
	

	☐
	Write vows and toasts
	
	

	☐
	
	
	



	WEEK OF


	☐
	To do
	Notes
	Due

	☐
	Final headcount to caterer
	
	

	☐
	Pack for the honeymoon
	
	

	☐
	Prepare vendor tips and payments
	
	

	☐
	Rehearsal and dinner
	
	

	☐
	Delegate the day-of list
	
	

	☐
	
	
	



Free to-do list template from Apollo's Templates — www.apollostemplates.com/to-do-lists/




